IMPLEMENTATION & PHASE PLAN  |  IMPL-RX-2026-001

ResolveX

Implementation & Phase Plan — Dual-Track Execution

A complete phase-by-phase implementation plan with dual-track task breakdown
(Track 1: AI/ML  |  Track 2: Backend, Frontend & UI),
covering workflows, goals, deliverables, and acceptance criteria for each phase.

| Document ID | IMPL-RX-2026-001 |
| --- | --- |
| References PRD | PRD-RX-2026-001 |
| Version | 1.0 |
| Total Phases | 4 Phases (0 through 3) |
| Total Duration | ~24 months (MVP in 6) |
| Team | Bugs — India Innovates 2026 |
| Last Updated | 2026 |

01.  Overview & Execution Philosophy

This document is the single source of truth for how ResolveX will be built. It translates the Product Requirements Document (PRD-RX-2026-001) into a concrete, time-bound, team-assignable execution plan structured across four phases.

## 1.1  Dual-Track Execution Model

All implementation work is organized into two parallel tracks that run simultaneously within each phase. This mirrors industry-standard engineering organization and prevents bottlenecks:

| ■ Track 1: AI / ML | ■ Track 2: BE / FE / UI | ■ BOTH: Parallel Tracks |
| --- | --- | --- |

- Track 1 (AI/ML) — covers all data science, machine learning, NLP, and analytics work. Tasks include dataset preparation, model training, evaluation, integration, and monitoring.

- Track 2 (BE/FE/UI) — covers all backend services, REST APIs, database schemas, frontend PWA, dashboard interfaces, and UX/UI design implementation.

- Both tracks converge at integration milestones where AI/ML model outputs plug into backend services.

## 1.2  Phase Overview

| Phase 0 Foundation (Weeks 1–3) | Phase 1 MVP (Weeks 4–24) | Phase 2 Intelligence (Months 7–12) | Phase 3 Scale (Months 13–24) |
| --- | --- | --- | --- |

| Phase | Duration | Core Deliverable | Success Gate |
| --- | --- | --- | --- |
| Phase 0 — Foundation | 3 weeks | Dev environment, schemas, CI/CD, wireframes | All engineers unblocked and contributing |
| Phase 1 — MVP | 5 months | Working complaint portal + auto-routing + live GIS map | Pilot city launch acceptance criteria passed |
| Phase 2 — Intelligence | 6 months | ML classifier + spatial clustering + risk engine + gamification | Predictive alerts firing; CSAT > 3.5 |
| Phase 3 — Scale | 12 months | Multi-city, computer vision, IoT, multilingual, open API | 3+ cities live; revenue contracts signed |

## 1.3  Engineering Principles

- API-first: all backend endpoints are specified and mocked before frontend development begins

- Feature flags: every new feature is deployed behind a flag to enable safe, incremental rollout

- Trunk-based development: short-lived feature branches merged to main within 2 days maximum

- Test-driven: unit tests written alongside feature code; integration tests before merge

- Continuous deployment: every merge to main deploys to staging automatically

02.  Phase 0 — Foundation & Setup (Weeks 1–3)

Phase 0 Foundation & Setup ¦ Target: End of Week 3 ✔ All team members have working local development environments ✔ PostgreSQL + PostGIS + MongoDB + Redis running in Docker Compose ✔ GitHub monorepo created with CI/CD pipeline (GitHub Actions) operational ✔ Complete database schema designed and seeded with sample data ✔ UI wireframes for all 5 core citizen flows approved ✔ AI/ML team has historical complaint dataset acquired and EDA complete

## 2.1  Phase 0 Goals & Objectives

- Remove all environmental and organizational blockers before feature development begins

- Establish shared conventions: API structure, naming, code style, Git workflow

- Deliver the database schema that all subsequent features will build upon

- Give AI/ML team the data and tooling to start the complaint labeling pipeline

- Give frontend team approved wireframes to begin UI implementation in Phase 1

## 2.2  Workflow

### Week 1 — Environment & Repository

- All engineers: clone monorepo template, configure local Docker Compose, verify services start

- DevOps: configure GitHub Actions CI pipeline (lint + test + build on push)

- DevOps: set up staging deployment target (Vercel for frontend, Render for backend services)

- AI/ML: acquire historical complaint dataset from pilot city (minimum 2,000 records)

### Week 2 — Schema & API Contracts

- Backend lead: write and review final PostgreSQL schema + PostGIS migration scripts

- Backend team: seed database with representative sample data for local development

- All engineers: agree on API request/response contract format (OpenAPI 3.0 spec template)

- AI/ML: begin Exploratory Data Analysis (EDA) on complaint dataset; generate distribution report

### Week 3 — Wireframes & Data Prep

- UI/UX: complete low-fidelity wireframes for all citizen-facing screens (5 flows)

- UI/UX: complete wireframes for admin dashboard main views

- UI/UX: team review and sign-off on wireframe set

- AI/ML: set up Jupyter notebook environment; run initial complaint text preprocessing pipeline

- AI/ML: complete labeling schema — finalize 8 categories and 40+ subcategories

## 2.3  Phase 0 Task Breakdown

| Task ID | Track | Task / Deliverable | Owner | Effort | Output / Artifact |
| --- | --- | --- | --- | --- | --- |
| P0-A01 | AI/ML | Dataset Acquisition & Audit Collect historical complaint records from pilot city; audit for completeness and PII | ML Eng | 3d | complaint_dataset.csv (2,000+ records) |
| P0-A02 | AI/ML | Exploratory Data Analysis (EDA) Analyze category distribution, text length, geographic spread, temporal patterns | ML Eng | 2d | EDA report + visualizations notebook |
| P0-A03 | AI/ML | Label Schema Design Define 8 categories, 40+ subcategories; write labeling guidelines for human annotators | ML Eng | 2d | labeling_schema.json + guidelines doc |
| P0-A04 | AI/ML | Text Preprocessing Pipeline Build NLTK tokenization, stop-word removal, TF-IDF vectorizer pipeline in Python | ML Eng | 3d | preprocessing.py module + unit tests |
| P0-B01 | BE/FE/UI | Monorepo & Git Workflow Setup Create GitHub org, monorepo structure, branch protection rules, PR templates | DevOps | 1d | GitHub repo with CONTRIBUTING.md |
| P0-B02 | BE/FE/UI | Docker Compose Dev Environment PostgreSQL+PostGIS, MongoDB, Redis, RabbitMQ all configured and start-verified | DevOps | 2d | docker-compose.yml + .env.example |
| P0-B03 | BE/FE/UI | CI/CD Pipeline (GitHub Actions) Lint, unit test, and build steps on every push to main; auto-deploy to staging | DevOps | 2d | .github/workflows/ CI/CD config |
| P0-B04 | BE/FE/UI | Database Schema & Migrations Write all PostgreSQL + PostGIS CREATE TABLE migrations with indexes and FK constraints | Backend | 3d | db/migrations/ (8 migration files) |
| P0-B05 | BE/FE/UI | Database Seed Data Seed script with test users, sample complaints, wards, departments, zones | Backend | 2d | db/seed.sql + seed runner |
| P0-B06 | BE/FE/UI | OpenAPI Spec Template Define API convention, auth header format, error schema, pagination standard | Backend | 1d | openapi-base.yaml |
| P0-B07 | BE/FE/UI | Citizen PWA Wireframes (5 flows) Lo-fi wireframes: Home, Report Issue, Confirmation, Track Status, Profile | UI/UX | 4d | Figma wireframe file (approved) |
| P0-B08 | BE/FE/UI | Admin Dashboard Wireframes Lo-fi wireframes: Task List, Complaint Detail, GIS Map, Analytics Overview | UI/UX | 3d | Figma wireframe file (approved) |

## 2.4  Phase 0 Exit Criteria

- All 12 tasks above marked Done with team sign-off

- Every engineer can run docker-compose up and see all services healthy

- CI pipeline passes on main branch with at least one test per service

- Wireframes reviewed and approved — no significant UX changes expected in Phase 1

03.  Phase 1 — MVP (Weeks 4–24  |  ~5 months)

Phase 1 Minimum Viable Product ¦ Target: End of Week 24 ✔ Citizens can file geo-tagged complaints with photo evidence in < 30 seconds ✔ Complaints automatically classified and routed to correct department (100% auto) ✔ SLA timers running; escalation notifications firing at 80% SLA consumption ✔ Admin dashboard with live feed, department workload, and GIS map operational ✔ Citizens receive push notification on every status change ✔ Pilot city deployment completed and passed all MVP acceptance criteria

## 3.1  Phase 1 Goals & Objectives

- Deliver a fully functional complaint-to-resolution workflow end-to-end

- Achieve 100% automated complaint routing with keyword-rule-based classifier (ML comes in Phase 2)

- Deploy live GIS map with all active complaints visible to administrators

- Complete all P0 functional requirements from PRD sections 5.1, 5.2, 5.3, and 5.5

- Pass all MVP launch acceptance criteria defined in PRD Section 10.1

- Onboard pilot city (1 municipal corporation, minimum 3 departments)

## 3.2  Phase 1 Sprint Structure

| Sprint | Weeks | Focus Area | Track Priority |
| --- | --- | --- | --- |
| Sprint 1 | 4–6 | Auth service: Phone OTP + OAuth + TOTP 2FA + SSO + role-picker PWA screen | BE/FE parallel start |
| Sprint 2 | 7–9 | Complaint submission API, GPS capture, media upload, PostGIS geo-validation | BE leads; FE PWA forms |
| Sprint 3 | 10–12 | Keyword classifier, routing engine, RabbitMQ queue, task creation | AI/ML + BE converge |
| Sprint 4 | 13–15 | SLA timer, escalation engine, notification service (WebSocket + email) | BE heavy |
| Sprint 5 | 16–18 | Leaflet.js GIS map, complaint markers, ward boundaries, admin dashboard v1 | FE heavy |
| Sprint 6 | 19–21 | Admin dashboard v2 (workload, SLA gauges), officer mobile task view | FE + BE |
| Sprint 7 | 22–23 | Integration testing, load testing, bug fixing, pilot city onboarding | Full team |
| Sprint 8 | 24 | Staging → Production deploy, pilot launch, acceptance testing | All |

## 3.3  Phase 1 Task Breakdown — Track 1: AI/ML

| Task ID | Track | Task / Deliverable | Owner | Effort | Output / Artifact |
| --- | --- | --- | --- | --- | --- |
| P1-A01 | AI/ML | Complaint Labeling Campaign Label 2,000 complaints across 8 categories using the Phase 0 schema. Use team annotation with inter-rater reliability check. | ML Eng | 10d | labeled_complaints.csv (2,000 rows) |
| P1-A02 | AI/ML | Keyword Rule-Based Classifier (MVP fallback) Build deterministic keyword lookup classifier for all 8 categories. This is the production classifier for Phase 1 while ML model is trained. | ML Eng | 5d | keyword_classifier.py + test suite (>90% accuracy on test set) |
| P1-A03 | AI/ML | SVM Text Classifier Training Train multi-class SVM on labeled data. Target: >80% accuracy. If missed, deploy keyword classifier and continue retraining. | ML Eng | 8d | complaint_classifier.pkl + evaluation_report.md |
| P1-A04 | AI/ML | Priority Scoring Formula Implementation Implement weighted priority formula: (Severity×0.4) + (Volume Index×0.3) + (Infra Age Risk×0.3). Output: integer 1–5. | ML Eng | 3d | priority_scorer.py + unit tests |
| P1-A05 | AI/ML | Duplicate Detection Algorithm PostGIS ST_DWithin(50m) + same category + timestamp < 48h window. Return duplicate flag + parent_id. | ML Eng | 4d | dedup_checker.py integrated in Complaint Service |
| P1-A06 | AI/ML | Classification Service API Wrap classifier + priority scorer in FastAPI microservice. POST /classify endpoint; response in < 3s. | ML Eng | 4d | classification-service/ (deployed to staging) |
| P1-A07 | AI/ML | Active Learning Feedback Loop Log all classification errors from officer corrections. Build pipeline to retrain model weekly on accumulated corrections. | ML Eng | 5d | active_learning_pipeline.py + scheduled retraining job |

## 3.4  Phase 1 Task Breakdown — Track 2: Backend, Frontend & UI

| Task ID | Track | Task / Deliverable | Owner | Effort | Output / Artifact |
| --- | --- | --- | --- | --- | --- |
| P1-B01 | BE/FE/UI | Auth Service Core (JWT RS256 + RBAC + refresh token rotation) JWT signing with RS256. Role middleware on all routes. HttpOnly refresh cookie. Token rotation. /auth/login /refresh /logout. Access token in memory, refresh in cookie. | Backend | 6d | auth-service/ OpenAPI spec + 80% test coverage |
| P1-B01A | BE/FE/UI | Phone OTP auth — request + verify endpoints POST /auth/otp/request: generate 6-digit OTP, bcrypt hash to Redis TTL=600s, dispatch via Twilio/MSG91. POST /auth/otp/verify: check hash, invalidate, upsert user, issue JWT. Rate limit 3 req/phone/15min. | Backend | 4d | otp endpoints + Redis OTP store + SMS integration tested |
| P1-B01B | BE/FE/UI | Google + Apple OAuth callbacks GET /auth/oauth/google/cb and POST /auth/oauth/apple/cb. Extract verified email from ID tokens. Upsert citizen user. Handle Apple relay email. Role always = citizen for OAuth. | Backend | 4d | OAuth callback endpoints + upsert logic tested |
| P1-B01C | BE/FE/UI | TOTP 2FA setup + verification (officer/dept head) POST /auth/login returns partial session. POST /auth/login/2fa verifies TOTP code (RFC 6238). TOTP secret stored encrypted. 10 backup codes generated at first setup (bcrypt hashed). | Backend | 5d | 2FA endpoints + backup code generation + TOTP validation |
| P1-B01D | BE/FE/UI | Commissioner SSO — SAML 2.0 + OIDC GET /auth/sso/saml and /auth/sso/oidc initiation. POST /auth/sso/saml/cb and GET /auth/sso/oidc/cb callbacks. Validate assertion/token, extract identity, issue commissioner JWT. Audit log to MongoDB. | Backend | 8d | SSO endpoints + SAML/OIDC libs configured + audit_events collection |
| P1-B01E | BE/FE/UI | Session management + revocation endpoints GET /auth/sessions — list own sessions. DELETE /auth/sessions/:id — revoke specific. POST /auth/sessions/revoke-all. Sessions stored in Redis keyed by jti. | Backend | 3d | session endpoints + Redis session store + revocation tested |
| P1-B01F | BE/FE/UI | Login error states + lockout policy (BE) Failed attempt counter per account in Redis. Lockout at attempt 3 (15min) and 5+ (IT helpdesk). IP rate limiting separate from account lockout. All errors return generic "Invalid credentials" (no enumeration). | Backend | 3d | lockout middleware + attempt counter + IP rate limiting |
| P1-B01G | BE/FE/UI | Role-picker entry screen (PWA) 4-card role selector as first screen. Cards: Citizen / Officer / Dept Head / Commissioner. Guest track-complaint link. Continue button routes to correct auth flow per role. Role pre-selected from last session. | Frontend | 2d | apps/citizen/app/(auth)/role-select/page.tsx + Next.js middleware routing |
| P1-B01H | BE/FE/UI | Citizen login screens — OTP + OAuth (PWA) Phone number entry with +91 prefix dropdown. OTP input (6 boxes, auto-fill via Web OTP API on Android). Countdown timer. Resend OTP. Google + Apple OAuth buttons. Error states: wrong OTP, expired OTP, lockout. | Frontend | 5d | apps/citizen/app/(auth)/login/page.tsx + otp/page.tsx — all states |
| P1-B01I | BE/FE/UI | Returning citizen welcome-back screen On app open: check refresh cookie. If valid: show welcome-back card with name + ward + points. One-tap sign-in. "Use different account" option. Session list view in profile. | Frontend | 2d | apps/citizen/app/(auth)/welcome/page.tsx + session list |
| P1-B01J | BE/FE/UI | Officer login screens — govID + password + TOTP (desktop/mobile) Govt badge label. Employee ID field. Password field with show/hide. TOTP screen with 6-box input. Backup code fallback. 2FA setup QR screen. Backup codes display screen (step 4 of activation). | Frontend | 5d | apps/admin/app/(auth)/login/page.tsx — staff login + 2FA + activation |
| P1-B01K | BE/FE/UI | Commissioner login — SSO buttons + fallback (desktop) High-privilege warning banner. "Sign in with State Govt SSO" button. "Sign in with NIC eGov SSO" button. Email + password fallback section. FIDO2 hardware key info panel. | Frontend | 3d | apps/admin/app/(auth)/login/commissioner/page.tsx — SSO screens |
| P1-B01L | BE/FE/UI | Post-login routing + citizen home screen layout After login: role-based redirect. Citizen home: Report button (primary CTA) + complaint list + ward mini-map tile + stats row (score/filed/resolved%). Welcome greeting with name + ward + points. | Frontend | 5d | apps/citizen/app/(dashboard)/home/page.tsx + Next.js middleware role router |
| P1-B02 | BE/FE/UI | Complaint Service — Core CRUD POST /complaints (create), GET /complaints/:id, PATCH /complaints/:id/status. PostGIS geo-validation on create. | Backend | 8d | complaint-service/ endpoints + integration tests |
| P1-B03 | BE/FE/UI | Media Upload Service S3-compatible multipart upload. MIME validation, virus scan stub, signed URL generation for retrieval. | Backend | 5d | media-service/ with upload + URL generation endpoints |
| P1-B04 | BE/FE/UI | GIS Service — Ward Boundaries Load ward GeoJSON into PostGIS. GET /zones/:wardId, POST /zones/lookup (coordinates → ward). ST_Within intersection. | Backend | 6d | gis-service/ with 3 endpoints + PostGIS ward table populated |
| P1-B05 | BE/FE/UI | Routing Engine (RabbitMQ consumer) Consumes complaint_classified queue. Runs workload balancing query. Creates Task record. Publishes to task_created queue. | Backend | 7d | routing-engine/ service + queue integration test |
| P1-B06 | BE/FE/UI | SLA Monitor & Escalation Engine Cron job every 15 min: scan tasks past 80% SLA; publish escalation event. Cron every hour: flag overdue as Escalated. | Backend | 5d | sla-monitor/ cron service + escalation event schema |
| P1-B07 | BE/FE/UI | Notification Service (WebSocket + Email) WebSocket server for real-time status push. Nodemailer email for escalation + resolution events. | Backend | 6d | notification-service/ + WebSocket client test harness |
| P1-B08 | BE/FE/UI | Design System & Component Library Tailwind config, color tokens, Button, Card, Badge, Input, Modal, Toast — Next.js compatible shared components (packages/ui). | UI/UX | 5d | packages/ui/ — shared Next.js components + Storybook |
| P1-B09 | BE/FE/UI | PWA — Citizen Complaint Filing Flow 5-screen flow: Home → Category → Location (GPS + map pin) → Evidence upload → Confirm. < 30s completion target. | Frontend | 10d | apps/citizen/app/(complaint)/ — 5 route segments; next-pwa offline support |
| P1-B10 | BE/FE/UI | PWA — Complaint Status Tracking GET /complaints/:id public page. Status timeline, department name, SLA indicator. Push notification registration. | Frontend | 5d | apps/citizen/app/track/[id]/page.tsx — SSR rendered for instant load; push SW |
| P1-B11 | BE/FE/UI | Admin Dashboard — Task Management Officer view: paginated task list with priority sort, SLA countdown, status update form, action notes input. | Frontend | 8d | apps/admin/app/tasks/page.tsx + [taskId]/page.tsx — task list + detail |
| P1-B12 | BE/FE/UI | Admin Dashboard — GIS Map View Leaflet.js map with OpenStreetMap tiles. Complaint markers (color by category). Ward boundary overlay toggle. IMPORTANT: import Leaflet as dynamic import with ssr:false — Leaflet uses window and breaks Next.js SSR. | Frontend | 6d | apps/admin/app/map/page.tsx — Leaflet dynamic import (ssr:false) + markers |
| P1-B13 | BE/FE/UI | Admin Dashboard — Department Workload Bar chart of open tasks per officer. SLA compliance gauge. Average resolution time metric card. | Frontend | 5d | apps/admin/app/analytics/page.tsx — 3 chart components |
| P1-B14 | BE/FE/UI | Load & Performance Testing k6 load test: 200 concurrent users, complaint submission flow. Target: p99 < 500ms API, < 2s dashboard load. | DevOps | 4d | k6 test scripts + performance test report |
| P1-B15 | BE/FE/UI | Security Audit (OWASP Top 10) Manual review of all API endpoints for injection, auth bypass, IDOR, rate limiting gaps. Fix all P0 findings. | Backend | 3d | security_audit_report.md + fixes committed |

## 3.4A  Auth Implementation Notes

The auth service (tasks P1-B01 through P1-B01L) is the expanded implementation of what prior documents called simply "Auth Service (JWT + RBAC)". The following 12 tasks replace the single original P1-B01 entry with full coverage of all auth flows identified during wireframe design.

- P1-B01 (core JWT + RBAC) must be done first — all other auth tasks depend on it

- P1-B01A (OTP) + P1-B01B (OAuth) + P1-B01C (TOTP) can be built in parallel after P1-B01

- P1-B01D (SSO for commissioner) is P1 priority — can be deferred to Sprint 2 without blocking MVP citizen/officer launch

- P1-B01G (role-picker screen) is a 2-day FE task that unblocks all login UI tasks — do it in Sprint 1 Week 1

- Combined auth effort: ~55 developer-days — accounts for Sprint 1 and part of Sprint 2

## 3.5  Phase 1 Integration Milestones

| Milestone | Week | Description | Success Criterion |
| --- | --- | --- | --- |
| INT-1: Auth ↔ All Services | 8 | JWT middleware deployed across all services | All protected endpoints return 401 for invalid tokens |
| INT-2: Complaint → Classification → Routing | 12 | End-to-end: submit → classify → route → task created | Task created within 10s of complaint submission in staging |
| INT-3: Task → Notification | 15 | Officer receives WebSocket alert + email on task assignment | Alert delivered within 2 min of task creation |
| INT-4: Status → Citizen Notification | 17 | Citizen push notification on every status change | Push delivered within 2 min of officer status update |
| INT-5: Full End-to-End | 22 | Complete complaint lifecycle: submit → resolve → citizen feedback | Lifecycle completes in staging with no manual intervention |

## 3.6  Phase 1 Exit Criteria (MVP Launch Gate)

- All P0 functional requirements from PRD Sections 5.1, 5.2, 5.3, and 5.5 implemented and tested

- All 10 MVP Launch Acceptance Criteria from PRD Section 10.1 pass in staging environment

- Load test: 200 concurrent users with p99 API < 500ms, no errors

- Security audit: zero P0 (critical/high) OWASP findings outstanding

- Pilot city onboarding complete: ward boundaries loaded, departments configured, officers trained

04.  Phase 2 — Intelligence Layer (Months 7–12)

Phase 2 Intelligence & Engagement Layer ¦ Target: End of Month 12 ✔ Production ML NLP classifier achieving >85% accuracy replacing keyword classifier ✔ DBSCAN spatial clustering running on 30-day rolling window in production ✔ Risk scores computed for all ward zones; early warning alerts firing to department heads ✔ Citizen reputation + gamification system live; ward leaderboard visible ✔ Post-resolution feedback collected; CSAT dashboard operational for administrators ✔ SLA compliance dashboard with department drill-down live

## 4.1  Phase 2 Goals & Objectives

- Replace rule-based keyword classifier with production ML model (>85% accuracy target)

- Activate the Urban Intelligence Engine with spatial clustering and risk scoring

- Ship the citizen engagement system (reputation, gamification, leaderboards)

- Deliver SLA compliance analytics and CSAT measurement infrastructure

- Implement complete P1 priority functional requirements from PRD

## 4.2  Phase 2 Task Breakdown — Track 1: AI/ML

| Task ID | Track | Task / Deliverable | Owner | Effort | Output / Artifact |
| --- | --- | --- | --- | --- | --- |
| P2-A01 | AI/ML | ML Model Expansion — More Training Data Collect and label 3,000+ additional complaints using active learning corrections from Phase 1 production data. | ML Eng | 10d | labeled_dataset_v2.csv (5,000+ total records) |
| P2-A02 | AI/ML | Model Benchmarking & Selection Compare SVM, Random Forest, and fine-tuned DistilBERT on Phase 1 + Phase 2 dataset. Select best F1 score model. | ML Eng | 8d | model_benchmark_report.md + selected model artifact |
| P2-A03 | AI/ML | Production Model v2 Deployment Replace keyword classifier with ML model in Classification Service. Gradual rollout: 10% → 50% → 100% traffic. | ML Eng | 5d | classifier v2 in production with rollout verified |
| P2-A04 | AI/ML | DBSCAN Spatial Clustering Pipeline Implement rolling 30-day complaint window. Tune epsilon (radius) and min_samples on pilot city data. Output: cluster polygons. | ML Eng | 10d | clustering_pipeline.py + cluster_zones PostGIS table |
| P2-A05 | AI/ML | Zone Risk Scoring Model Compute risk score (0–100) per zone: cluster density + complaint severity + infrastructure age + historical frequency. | ML Eng | 8d | risk_scorer.py + zone_risk_scores table + scoring docs |
| P2-A06 | AI/ML | Early Warning Alert Engine Threshold monitor: if zone risk score crosses 60/80/95 → generate alert event for Notification Service. | ML Eng | 5d | alert_engine.py + alert integration test with Notification Svc |
| P2-A07 | AI/ML | Seasonal Risk Model (IMD Integration) Fetch IMD historical rainfall data. Build regression model linking rainfall + drainage complaint volume for monsoon prediction. | ML Eng | 10d | seasonal_model.py + IMD data pipeline |
| P2-A08 | AI/ML | Model Monitoring & Drift Detection Log prediction confidence weekly. Alert if accuracy drops below 80% threshold → trigger retraining. | ML Eng | 5d | model_monitor.py + Grafana/Datadog dashboard |
| P2-A09 | AI/ML | Reputation Score Algorithm Define point scoring: +10 per verified complaint, +25 per infrastructure improvement linked, −5 per false report. Compute weekly. | ML Eng | 4d | reputation_scorer.py + reputation computation cron job |

## 4.3  Phase 2 Task Breakdown — Track 2: Backend, Frontend & UI

| Task ID | Track | Task / Deliverable | Owner | Effort | Output / Artifact |
| --- | --- | --- | --- | --- | --- |
| P2-B01 | BE/FE/UI | Analytics Service — Cluster API GET /analytics/clusters: returns active DBSCAN cluster GeoJSON polygons with risk level and complaint count. | Backend | 5d | analytics-service/clusters endpoint + GeoJSON schema |
| P2-B02 | BE/FE/UI | Analytics Service — Risk Score API GET /analytics/risk-zones: returns all ward zones with current risk score, trend (improving/worsening), and alert level. | Backend | 4d | analytics-service/risk-zones endpoint + OpenAPI spec |
| P2-B03 | BE/FE/UI | Admin Dashboard — Risk Map Layer Add risk heatmap layer to Leaflet.js map. Zones colored by risk level (green/amber/red/dark-red). Toggle controls. | Frontend | 6d | apps/admin/app/map/page.tsx — risk heatmap layer added |
| P2-B04 | BE/FE/UI | Admin Dashboard — Early Warning Panel Sidebar panel showing active risk alerts: zone name, risk level, key metrics, recommended action button. | Frontend | 5d | apps/admin/app/alerts/page.tsx — alert panel |
| P2-B05 | BE/FE/UI | Admin Dashboard — SLA Compliance View SLA compliance % by department (bar chart). Escalation log. Officer-level SLA breakdown. Date range filter. | Frontend | 6d | apps/admin/app/sla/page.tsx — SLA analytics |
| P2-B06 | BE/FE/UI | Admin Dashboard — CSAT View Average satisfaction score by department and category. Distribution histogram. Word cloud from feedback text. | Frontend | 5d | apps/admin/app/csat/page.tsx — satisfaction analytics |
| P2-B07 | BE/FE/UI | Citizen Reputation & Profile Page Citizen profile: score, badges earned, complaint count, verification rate, position on ward leaderboard. | Frontend | 5d | apps/citizen/app/(dashboard)/profile/page.tsx — reputation + badges |
| P2-B08 | BE/FE/UI | City & Ward Leaderboard Public leaderboard: top 10 citizen reporters by ward and city-wide. Weekly and all-time toggle. | Frontend | 4d | apps/citizen/app/(dashboard)/leaderboard/page.tsx |
| P2-B09 | BE/FE/UI | Post-Resolution Feedback Flow On resolution: citizen gets feedback prompt (push + in-app). 5-star rating + optional text. Stored and aggregated. | Frontend | 4d | apps/citizen/app/(dashboard)/feedback/page.tsx + API route |
| P2-B10 | BE/FE/UI | Notification Service — Risk Alert Dispatch Consume risk alert events from AI engine. Send WebSocket alert to Commissioner and Department Head role users. | Backend | 4d | notification-service/ — risk alert event handler |
| P2-B11 | BE/FE/UI | Complaint Re-Routing Workflow Officer can reject task (with reason). Routing engine reassigns to next eligible officer in same department. | Backend | 4d | routing-engine/ — rejection + reassignment flow |
| P2-B12 | BE/FE/UI | Analytics Export (PDF + CSV) Dashboard export: generate PDF report of selected date range metrics. CSV export for raw complaint data. | Backend | 5d | export-service/ — PDF generator (Puppeteer) + CSV endpoint |

## 4.4  Phase 2 Exit Criteria

- ML classifier in production at >85% category accuracy on validation set

- DBSCAN clustering running nightly; cluster polygons visible on admin map

- Risk scores updated daily for all ward zones; at least 1 real early warning alert issued in pilot city

- Citizen reputation system live; leaderboard showing at least 50 active users

- CSAT score measured for pilot city; target: >3.5 / 5.0

- All P1 functional requirements from PRD implemented and Definition-of-Done verified

05.  Phase 3 — Scale & Platform Expansion (Months 13–24)

Phase 3 Scale & Advanced Intelligence ¦ Target: End of Month 24 ✔ 3+ cities live on ResolveX with isolated data environments ✔ Computer vision model detecting potholes, waterlogging, and debris from uploaded images ✔ IoT sensor data integrated for drainage and water level monitoring in at least 1 zone ✔ Multilingual PWA: Hindi + 2 regional languages supported ✔ Open REST API available for third-party municipal app integration ✔ Revenue contracts signed with at least 2 municipal corporations

## 5.1  Phase 3 Goals & Objectives

- Scale infrastructure to support multi-city deployment with per-city data isolation

- Introduce computer vision for automatic defect detection from complaint images

- Begin IoT sensor integration for real-time environmental monitoring overlay

- Launch multilingual support (Hindi + regional languages) for broader citizen reach

- Open API ecosystem for third-party integration and government ERP connectivity

- Achieve commercial revenue milestones: 2+ signed municipal SaaS contracts

## 5.2  Phase 3 Task Breakdown — Track 1: AI/ML

| Task ID | Track | Task / Deliverable | Owner | Effort | Output / Artifact |
| --- | --- | --- | --- | --- | --- |
| P3-A01 | AI/ML | Computer Vision — Defect Detection Model Fine-tune MobileNetV3 on labeled complaint images: potholes, waterlogging, garbage, damaged roads. Target: >80% mAP. | ML Eng | 20d | cv_defect_model.pt + image_classifier FastAPI endpoint |
| P3-A02 | AI/ML | CV Model Integration with Complaint Service On image upload: run CV inference async. Auto-tag complaint with detected defect types. Flag for officer if confidence > 0.7. | ML Eng | 8d | cv_inference job in media pipeline + tag schema in complaints table |
| P3-A03 | AI/ML | IoT Data Ingestion Pipeline Build MQTT broker connector. Define sensor schema for water level + drainage flow sensors. Ingest into time-series store. | ML Eng | 15d | iot-bridge/ service + sensor_readings table (TimescaleDB) |
| P3-A04 | AI/ML | IoT + Complaint Data Fusion Correlate sensor anomalies with nearby complaint clusters. If water level spike + drainage complaints → elevate risk score. | ML Eng | 10d | data_fusion.py + enriched risk score model v3 |
| P3-A05 | AI/ML | Multi-City Model Adaptation Add city_id dimension to all models. Train city-specific classifiers for cities with distinct terminology. Federated model updates. | ML Eng | 12d | multi_city_classifier.py + per-city model registry |
| P3-A06 | AI/ML | NLP Multilingual Support Extend text classifier to handle Hindi + Tamil + Telugu inputs using multilingual DistilBERT or XLM-RoBERTa. | ML Eng | 15d | multilingual_classifier.py + accuracy report per language |
| P3-A07 | AI/ML | Predictive Maintenance Schedule Generator Monthly report: rank zones by predicted failure likelihood in next 60 days. Export to admin dashboard + PDF. | ML Eng | 10d | maintenance_scheduler.py + monthly report generation pipeline |

## 5.3  Phase 3 Task Breakdown — Track 2: Backend, Frontend & UI

| Task ID | Track | Task / Deliverable | Owner | Effort | Output / Artifact |
| --- | --- | --- | --- | --- | --- |
| P3-B01 | BE/FE/UI | Multi-City Data Architecture Add city_id tenant scoping to all tables. Row-level security policies in PostgreSQL. Per-city API key namespace. | Backend | 10d | db migration: city_id on all tables + RLS policies |
| P3-B02 | BE/FE/UI | City Onboarding Admin Panel Super-admin UI for creating new city tenant: upload ward GeoJSON, configure departments, set branding, invite admin. | Frontend | 10d | apps/super-admin/ — city setup wizard (5-step flow) |
| P3-B03 | BE/FE/UI | Multilingual PWA (i18n) next-intl integration. Hindi + Tamil translation files (messages/hi.json, messages/ta.json). Language toggle using Next.js middleware locale detection. | Frontend | 8d | messages/hi.json + messages/ta.json + middleware locale routing |
| P3-B04 | BE/FE/UI | Open REST API & Developer Portal Public API gateway with API key auth. Rate limiting for external consumers. Developer docs (Swagger UI) public deployment. | Backend | 10d | api.resolvex.in/docs — public API portal live |
| P3-B05 | BE/FE/UI | IoT Sensor Map Layer Add sensor overlay to admin GIS map: water level and drainage flow sensor locations with live readings tooltip. | Frontend | 6d | apps/admin/app/map/page.tsx — IoT sensor overlay layer |
| P3-B06 | BE/FE/UI | CV Defect Tag Display Show CV-detected defect tags on complaint detail page for officers. Confidence score + manual override option. | Frontend | 4d | apps/admin/app/complaints/[id]/page.tsx — CV tag display |
| P3-B07 | BE/FE/UI | Predictive Maintenance Report UI Monthly report page in admin dashboard: ranked zone list with risk trend chart and recommended action items. | Frontend | 6d | apps/admin/app/maintenance/page.tsx — report + next/dynamic PDF |
| P3-B08 | BE/FE/UI | Enterprise SLA Dashboard (Commissioner) Executive view: city-wide KPI summary, cross-department comparison, risk alert feed, PDF report generation. | Frontend | 8d | apps/admin/app/executive/page.tsx — commissioner view (SSR KPIs) |
| P3-B09 | BE/FE/UI | ERP Integration Adapter Framework Pluggable webhook/API adapter for municipal ERP systems. Config-driven: endpoint URL, auth type, field mapping. | Backend | 12d | integrations/erp-adapter/ — webhook framework + docs |
| P3-B10 | BE/FE/UI | Security Penetration Test (External) Engage external security firm for full penetration test. Resolve all Critical and High findings before Phase 3 launch. | DevOps | 10d | pentest_report.pdf + all Critical/High findings resolved |
| P3-B11 | BE/FE/UI | Disaster Recovery & Backup Testing Simulate database failure; verify restore from backup in < 4 hours. Document recovery runbook. | DevOps | 5d | DR_runbook.md + restore drill completed and documented |

## 5.4  Phase 3 Exit Criteria

- 3+ cities live with fully isolated data environments and per-city admin panels

- Computer vision model tagging defects in >70% of uploaded complaint images in production

- IoT sensor integration live in at least 1 pilot zone with sensor data visible on admin map

- Hindi language support live in PWA with at least 100 Hindi-language complaints filed

- Public API portal live with at least 2 registered third-party integration partners

- 2+ signed commercial SaaS contracts with municipal corporations

06.  Cross-Phase Workflows & Governance

## 6.1  Sprint Cadence (All Phases)

- Sprint length: 2 weeks

- Sprint planning: Monday morning, Week 1 of sprint — review backlog, assign tasks, confirm capacity

- Daily standup: 15 minutes — what did you do yesterday, what are you doing today, any blockers

- Sprint review: Friday afternoon, Week 2 — demo working features to full team

- Sprint retrospective: Friday afternoon, Week 2 (after review) — process improvements

- Backlog refinement: Wednesday, Week 1 — groom upcoming sprint items, clarify acceptance criteria

## 6.2  Definition of Ready (Before a Task Enters a Sprint)

- Acceptance criteria clearly written in the task ticket

- Dependencies on other tasks explicitly identified

- API contract (if applicable) specified in OpenAPI format

- Effort estimate agreed by the assigned engineer

- No unresolved blockers at ticket creation time

## 6.3  Code Review Standards

- All pull requests require review by at least 1 other engineer before merge

- PR must include: test coverage for new code paths, passing CI, no linting errors

- PRs should be < 400 lines of diff — large changes broken into multiple PRs

- Review turnaround SLA: within 1 business day

## 6.4  Track Synchronization Points

AI/ML Track and BE/FE/UI Track must coordinate at the following interface points in every phase:

| Interface Point | When | What Gets Handed Over |
| --- | --- | --- |
| Classification API Contract | Sprint before ML model is needed | OpenAPI spec for POST /classify — request + response schema |
| Model Artifact Handoff | When model accuracy target is hit | .pkl or .pt model file + inference wrapper + performance report |
| Risk Score Schema | Before analytics dashboard is built | JSON schema for zone risk objects + threshold definitions |
| Active Learning Feedback Format | After Phase 1 launch | CSV format for officer corrections → ML team for retraining input |
| CV Tag Schema | Before CV tags shown in dashboard | JSON schema for image defect tags + confidence score format |

## 6.5  Quality Gates Between Phases

| Gate | Timing | Required Attendees | Go / No-Go Criteria |
| --- | --- | --- | --- |
| Phase 0 → Phase 1 | End of Week 3 | Full team + Product Lead | All Phase 0 exit criteria met; no team member is blocked |
| Phase 1 → Phase 2 | End of Month 6 | Full team + pilot city rep | All MVP acceptance criteria pass in staging; pilot city signed off |
| Phase 2 → Phase 3 | End of Month 12 | Team + Product Lead + first city admin | CSAT > 3.5; ML accuracy > 85%; revenue pipeline confirmed |
| Phase 3 Exit | End of Month 24 | All stakeholders | 3+ cities live; 2+ contracts; CV + IoT milestones met |

## 6.6  Risk Escalation Protocol

- Engineer identifies a blocker: raises in daily standup same day

- Blocker unresolved after 24 hours: Product Lead + relevant track lead hold focused 30-min resolution session

- Blocker threatens sprint goal after 48 hours: scope trade-off decision made — defer a P1 to next sprint

- Blocker threatens phase exit gate: emergency team review; options — phase extension, scope reduction, or external help

## 6.7  Next.js Frontend Conventions (Updated from React + Vite)

Both frontend apps (citizen PWA and admin dashboard) are built with Next.js 14 App Router. The following conventions apply across all frontend tasks to ensure consistency and avoid common Next.js-specific pitfalls.

### App Router structure — route groups

- Citizen app route groups: (auth) for login/OTP/welcome screens, (complaint) for the filing flow, (dashboard) for home/profile/track. Groups do not appear in the URL.

- Admin app route groups: (auth) for staff login screens, (officer) for task queue views, (head) for dept views, (commissioner) for city command views. Role-based access enforced by middleware.

### Server vs client components — rule of thumb

| Component Type | When to Use | Examples |
| --- | --- | --- |
| Server Component (default) | Data fetching, static content, pages that benefit from SSR/SSG | Complaint status tracking page (/track/[id]) — server-renders complaint data for instant load and SEO; Commissioner KPI cards fetched at render time |
| Client Component ("use client") | Interactivity, browser APIs, state, event handlers | Complaint filing form (GPS access, photo upload, form state); Leaflet map; OTP input boxes; real-time polling with TanStack Query |
| Server Action | Form submissions that mutate server data without a full API round-trip | Complaint submission, status updates, feedback ratings |

### Critical: Leaflet.js must use dynamic import with ssr:false

Leaflet SSR Fix — Required for All Map Components Leaflet.js directly accesses window and document on import. This crashes Next.js SSR. Every component that uses Leaflet MUST be imported as: const MapComponent = dynamic(() => import('@/components/Map'), { ssr: false }) Never import Leaflet at the top of a page or layout file. Always wrap in a loading state: { loading: () => <MapSkeleton /> }

### PWA setup — next-pwa

- Install next-pwa and wrap next.config.js with withPWA(). Service worker is auto-generated on build.

- Manifest file at /public/manifest.json — defines PWA name, icons, theme colour, display: standalone.

- Offline support: cache complaint filing form data in IndexedDB (idb-keyval) so a draft survives network loss.

- The track/:id status page intentionally does NOT use offline cache — always fetches live status.

### Authentication — Next.js middleware

- middleware.ts at root intercepts every request. Reads access token from Authorization header (API calls) or validates refresh cookie (browser navigation).

- Unauthenticated requests to protected routes redirect to /login — no client-side auth check needed in page components.

- Role routing: middleware reads role from JWT, redirects to correct post-login destination automatically.

- Public routes that bypass middleware: /track/[id], /api/auth/*, /api/health — configured in middleware matcher.

### Shared component library — packages/ui

- Built with Tailwind CSS and CVA (Class Variance Authority) for typed component variants. Example: <Button variant="primary" size="sm">.

- All components are Server Component compatible by default — only marked "use client" if they need event handlers or hooks.

- Storybook configured in packages/ui for visual testing of all components before integration.

07.  Tools, Stack & Team Conventions

## 7.1  Toolchain Reference

| Category | Tool | Purpose |
| --- | --- | --- |
| Project Management | Linear / Jira | Sprint boards, backlog, task tracking, velocity metrics |
| Documentation | Notion | PRD, architecture decisions, meeting notes, onboarding guides |
| Design | Figma | Wireframes, high-fidelity UI mockups, design system, prototypes |
| Version Control | GitHub (monorepo) | All code, CI/CD configuration, PR reviews, branch policies |
| CI/CD | GitHub Actions | Automated lint, test, build, deploy on every push to main |
| Containers | Docker + Docker Compose | Local dev environment; service containerization |
| Frontend Framework | Next.js 14 (App Router) | SSR + SSG + API Routes + PWA; both apps use Next.js |
| Frontend Styling | Tailwind CSS 3 | Utility-first; same config shared via packages/ui/ |
| Frontend State | TanStack Query + Zustand | Server state (TanStack) + client state (Zustand) |
| Frontend Deploy | Vercel | Next.js-native hosting; preview deployments per PR; Edge runtime |
| Backend Deploy | Render / Railway | Node.js and FastAPI microservice hosting |
| Observability | Sentry + Grafana | Error tracking, API latency dashboards, alerting |
| Load Testing | k6 | Performance and concurrent user testing for all API endpoints |
| API Documentation | Swagger UI (OpenAPI 3.0) | Auto-generated interactive API docs for all services |
| ML Experimentation | Jupyter + MLflow | Model training notebooks, experiment tracking, model registry |
| Communication | Slack | Daily coordination, CI/CD alerts, PR notifications, async discussion |

## 7.2  Monorepo Structure

Repository Layout apps/citizen/ → Next.js 14 PWA for citizens (App Router + next-pwa + Tailwind) apps/admin/ → Next.js 14 admin dashboard (App Router + Tailwind) services/auth-service/ → Node.js JWT authentication service services/complaint-service/ → Node.js complaint CRUD + geo-validation services/routing-engine/ → Node.js RabbitMQ consumer + task creation services/gis-service/ → Node.js PostGIS spatial query wrapper services/notification-service/ → Node.js WebSocket + email service services/media-service/ → Node.js S3-compatible media upload services/classification-service/ → FastAPI (Python) NLP classifier services/analytics-service/ → FastAPI (Python) clustering + risk scoring packages/ui/ → Shared Next.js-compatible component library (Tailwind + CVA) packages/api-client/ → Auto-generated TypeScript API client db/migrations/ → PostgreSQL migration files (numbered) db/seed/ → Development seed data ml/ → Jupyter notebooks, model artifacts, pipelines infra/ → Docker Compose, Nginx config, cloud IaC .github/workflows/ → CI/CD GitHub Actions configuration

ResolveX  |  IMPL-RX-2026-001  |  Team Bugs  |  India Innovates 2026

Implementation & Phase Plan  |  Version 1.0  |  Dual-Track Execution Model

## 07.  6-Day Hackathon Sprint Plan (March 19 to 24, 2026)  ★ NEW — v2.0

NON-NEGOTIABLE RULES FOR ALL TEAM MEMBERS - Feature freeze: March 24, 09:00 AM. Zero new features after this point. Bug fixes only. - Deploy to cloud (Railway, Render, or Fly.io) before end of Day 6. - Test the complete demo on 4G mobile, not WiFi, before departure on March 25. - Every team member must be able to deliver the full demo independently without assistance. - The monsoon scenario must run flawlessly before Day 5 ends. This is non-negotiable.

### 7.1  Day 1: March 19 - Foundation

Goal: Every engineer unblocked by end of day. Seed data schema ready. Map renders locally on all machines.

| BE / DevOps | Monorepo plus Docker Compose plus .env.example (P0-B01, P0-B02). PostgreSQL plus PostGIS running. 10 migration files including new v2.0 schema fields: source, officer_verified, secondary_issues. CI/CD GitHub Actions pipeline (RX-003). |
| --- | --- |
| AI / ML | Dataset acquired: minimum 500 complaint records from open civic data or synthetic generation. Label schema finalized for all 10 categories. EDA notebook started with distribution analysis. |
| FE | Next.js 14 scaffold with Tailwind CSS and Leaflet.js installed. 4 dummy routes rendering correctly. Role-picker screen built with Demo Citizen button visible in demo mode and hidden in production mode. |
| ALL | Seed SQL drafted: 60 complaints across 3 wards, monsoon scenario structure with 18 drainage complaints, 2 risk zone markers. Ready for Day 5 data loading. |
| Exit check | docker-compose up succeeds for every engineer. Map renders on localhost. All DB migrations pass clean. Entire team on the same git commit. |

### 7.2  Day 2: March 20 - Auth, Complaint Filing, and Multi-Issue Detection

Goal: A visitor can file a complaint end-to-end in under 45 seconds. Multi-issue detection card visible on photo upload.

| BE | JWT auth service plus RBAC (RX-004). Demo citizen one-tap login endpoint (RX-004D). Complaint CRUD plus geo-validation plus Bharat Mandapam geo-fence bounding box (RX-005, RX-014G). Media upload to local volume (RX-006). |
| --- | --- |
| AI / ML | Multi-issue detection lookup table plus POST /detect endpoint (RX-007M). Keyword classifier development starts (RX-007). Secondary issues stored in complaints.secondary_issues JSONB field. |
| FE | Role-picker with Demo Citizen button (RX-019D). Complaint filing 5-screen flow (RX-012). Sandbox mode amber banner throughout filing flow (RX-012S). Multi-issue detection UI card with confidence bars. Category-first filing enforced before description field appears. |
| Exit check | File complaint on mobile in under 45 seconds. Record appears in DB with GPS coordinates. Detection card shows 2 secondary issues automatically. Sandbox banner visible throughout the entire flow. |

### 7.3  Day 3: March 21 - AI Routing and Live GIS Map

Goal: Complaint filed, classified, routed, and hollow pin appears on admin map in under 3 seconds. This is the crowd magnet at the booth.

| AI / ML | Keyword classifier ships to production as P0 fallback (RX-007). Duplicate detection using PostGIS ST_DWithin for 50m radius and 48-hour window (RX-008). SVM training pipeline starts on labeled dataset. |
| --- | --- |
| BE | RabbitMQ routing engine fully wired: complaint to classifier to department assignment to task created (RX-009). Demo reset endpoint DELETE /admin/demo/reset (RX-015R). |
| FE | Leaflet map with live complaint pins appearing as filed, color-coded by category (RX-015). Dual marker system: solid for pre-seeded data, hollow/dashed for visitor-filed sandbox complaints (RX-015M). Map legend permanently visible. Admin complaint list with live feed (RX-016). Ctrl+Shift+R keyboard handler connected to reset endpoint. |
| Exit check | File complaint on phone. Hollow pin appears on admin map in under 3 seconds. Demo reset clears all sandbox complaints and restores seed data in under 5 seconds. Demo is confidently showable to a stranger. |

### 7.4  Day 4: March 22 - SLA, Notifications, Officer View, and Trust Layer

Goal: Close the full loop. Citizen files, officer receives task, officer verifies on ground, hollow marker turns solid, citizen gets notified.

| BE | SLA timer cron job plus escalation notifications (RX-010): P1=24h, P2=48h, P3=72h. WebSocket plus mock email notification service (RX-011). Officer verification endpoint POST /complaints/:id/verify that sets officer_verified=true and broadcasts WebSocket event (RX-T02). |
| --- | --- |
| AI / ML | DBSCAN clustering pipeline running on seed data (RX-021). Zone risk scoring computation begins targeting monsoon scenario detection (RX-022). |
| FE | Citizen complaint status tracking page with live status trail (RX-013). Officer task queue with SLA countdown bar and 3-action card showing Start, Resolve, and Verify options (RX-016, RX-018). Real-time marker transition from hollow to solid on officer verification WebSocket event. |
| Exit check | Full loop working: citizen files, officer gets task notification, officer verifies, marker turns solid live on admin screen. Citizen tracking page shows 'Verified on ground' in status trail. |

### 7.5  Day 5: March 23 - Risk Intelligence, Seed Data, and Full Rehearsal

Goal: Monsoon scenario runs flawlessly. Every team member can demo independently. The product is finals-ready.

| AI / ML | Zone risk scoring finalised (RX-022). Early warning engine: Ward 7 triggers HIGH risk alert automatically (RX-023). Monsoon scenario: 18 drainage complaints clustered correctly, heatmap overlay shows red zone. |
| --- | --- |
| FE | Risk heatmap overlay on admin GIS map (RX-024). SLA compliance gauge and percentage indicator (RX-026). Department workload bars showing officer distribution (RX-017). Commissioner view complete: all departments, risk alert panel, city-wide statistics. |
| ALL | Load 60 seed complaints into production cloud DB. Monsoon scenario seeded and verified with solid markers. Demo reset tested on live deployment. End-to-end demo rehearsal conducted 3 times with a different team member presenting each time. |
| Exit check | Monsoon scenario: Ward 7 appears red on heatmap. Commissioner view shows all departments and risk alert panel populated. Every team member completes a solo demo run in under 6 minutes without assistance. |

### 7.6  Day 6: March 24 - Freeze, Deploy, Pitch, and Pack

| 09:00 FEATURE FREEZE | Zero new code from this moment. Announce to all team members. Only bug fixes are permitted after this time. |
| --- | --- |
| Morning | Deploy to Railway, Render, or Fly.io. Obtain public HTTPS URL. Test entire demo on 4G mobile only, not WiFi. Fix any deployment-specific bugs as these qualify as fixes. |
| Afternoon | Record 90-second backup screen capture as MP4 file on tablet. Print 50 QR cards, 2 A3 posters, and 10 financial summary sheets. Export pitch deck as PDF for offline use. |
| Evening | Booth pitch rehearsal 3 times with every team member presenting. Pack all equipment. Rest adequately. Complete travel preparations for March 25 departure. |
| Exit check | Public HTTPS URL live and demo works on 4G. Every team member demos independently in under 6 minutes. Monsoon scenario loads correctly on first visit. Demo reset confirmed working on the live cloud deployment. |

## 08.  New Task Register: v2.0 Additions  ★ NEW — v2.0

The following tasks are additions to the original task register in Sections 3 and 4 above. All P0 tasks must be completed within the 6-day sprint. P1 tasks are Phase 2 production targets.

### 8.1  Demo Mode Tasks: All P0

| RX-004D | Demo citizen one-tap login ¦ PH1 ¦ BE/FE ¦ P0 ¦ 2d ¦ dep: RX-004 |
| --- | --- |
| RX-007M | Multi-issue detection engine: rule-based lookup table plus POST /detect ¦ PH1 ¦ AI_ML ¦ P0 ¦ 4d ¦ dep: RX-007 |
| RX-012S | Sandbox mode amber banner plus demo UX throughout complaint filing flow ¦ PH1 ¦ FE ¦ P0 ¦ 2d ¦ dep: RX-012, RX-004D |
| RX-014G | Geo-fence to Bharat Mandapam demo ward bounding box ¦ PH1 ¦ BE ¦ P0 ¦ 1d ¦ dep: RX-014 |
| RX-015M | Dual marker system: solid for verified, hollow/dashed for sandbox ¦ PH1 ¦ FE ¦ P0 ¦ 2d ¦ dep: RX-015 |
| RX-015R | Demo reset endpoint plus Ctrl+Shift+R keyboard shortcut ¦ PH1 ¦ BE/FE ¦ P0 ¦ 1d ¦ dep: RX-015M |

### 8.2  Trust Architecture Tasks

| RX-T01 | Citizen reputation score table plus lifecycle event scoring logic ¦ PH1 ¦ BE ¦ P0 ¦ 2d ¦ dep: RX-005 |
| --- | --- |
| RX-T02 | Officer field verification: POST /complaints/:id/verify, triggers hollow-to-solid transition ¦ PH1 ¦ BE/FE ¦ P0 ¦ 2d ¦ dep: RX-016 |
| RX-T03 | Trust weight filter on DBSCAN input query ¦ PH2 ¦ AI_ML ¦ P1 ¦ 2d ¦ dep: RX-021, RX-T01 |
| RX-T04 | Reputation badge UI plus Trusted Reporter indicator on citizen profile and map ¦ PH2 ¦ FE ¦ P1 ¦ 3d ¦ dep: RX-T01 |

### 8.3  Phase 2 New Tasks Added in v2.0

| RX-022C | CV multi-issue detection using YOLO v8, replaces RX-007M in Phase 2 ¦ PH2 ¦ AI_ML ¦ P1 ¦ 12d ¦ dep: RX-019 |
| --- | --- |
| RX-033 | WhatsApp Business bot integration as India-first filing channel ¦ PH2 ¦ BE ¦ P1 ¦ 10d ¦ dep: RX-009, RX-007 |
| RX-034 | Field officer mobile app with GPS-stamped resolution photo upload ¦ PH2 ¦ FE ¦ P1 ¦ 8d ¦ dep: RX-016, RX-018 |
| RX-043 | Ward councillor dashboard for elected representatives ¦ PH3 ¦ FE ¦ P2 ¦ 6d ¦ dep: RX-018 |

## 09.  Scope Cuts: Deferred to Roadmap  ★ NEW — v2.0

The following features are explicitly excluded from the 6-day sprint scope. Mention all of them in the pitch presentation as Phase 2 or Phase 3 roadmap items. Judges at national hackathons respect a team that clearly knows its scope boundaries.

| Gamification and leaderboard | Phase 2: RX-028 and RX-029. Mention as citizen engagement layer in pitch. |
| --- | --- |
| CSAT dashboard | Phase 2: RX-027. Mention as measurement infrastructure for municipal administrators. |
| Analytics PDF and CSV export | Phase 2: RX-031. Mention for government audit report requirements. |
| Commissioner SSO and SAML | Phase 2: requires government identity provider configuration for each city. |
| Apple Sign In | Phase 2: requires paid Apple Developer account. Google OAuth sufficient for MVP. |
| Multilingual PWA | Phase 3: Hindi and regional languages. Mention for India-wide reach story. |
| IoT sensor ingestion | Phase 3: RX-036. Mention as smart city data overlay layer. |
| Open REST API portal | Phase 3: RX-038. Mention for third-party integration and ecosystem play. |
| Historical complaint replay map | Phase 3: RX-042. Mention as urban planning tool for administrators. |
| Full CV defect model | Phase 3: RX-035. Use rule-based for demo and explain clear upgrade path. |
| WhatsApp Business bot | Phase 2: RX-033. Mention prominently as India-first roadmap feature. |
| Ward councillor dashboard | Phase 3: RX-043. Mention for political will and accountability story. |

## 10.  Booth Operations Checklist  ★ NEW — v2.0

### 10.1  Pre-Departure Checklist (March 24 and 25)

- Feature freeze confirmed across all team members: no new commits after 09:00 March 24

- Public HTTPS URL live and tested on 4G mobile, not WiFi, before packing

- Seed data loaded on live deployment: 60 complaints, monsoon scenario, 2 risk zones, all verified

- Demo reset tested on live deployment: Ctrl+Shift+R gives clean map in under 5 seconds

- Dual markers verified: solid for pre-seeded data, hollow/dashed for visitor-filed complaints

- Multi-issue detection card shows correctly in complaint filing flow

- Officer verification tested: hollow to solid marker transition works live on admin screen

- Demo citizen login: one tap, no OTP, JWT issued in under 3 seconds

- 90-second backup screen recording exported as MP4 on tablet

- 50 QR cards printed. 2 A3 posters printed. 10 financial summary sheets printed.

- Every team member completes a solo demo run under 6 minutes without any assistance

### 10.2  Booth Day Checklist (March 28)

- Personal hotspot active before booth opens: never use venue WiFi under any circumstances

- Admin map visible on laptop screen from 3 or more metres away: crowd magnet active

- Tablet ready with citizen PWA loaded and logged in as demo citizen before visitors arrive

- QR cards stacked on table: hand one to every visitor immediately after demo

- Opening line ready: 'This map shows Ward 7 right now. 18 drainage complaints in 30 days. Our AI predicts 76% flood risk before monsoon. Want to file a complaint and watch it appear on the map?'

- Reset map before every new visitor cluster or before any VIP or judge approaches

- Show Demo Citizen button first: never make a judge type an OTP code

- When asked 'is this real?': point to sandbox banner, explain three-layer trust architecture, live-verify a marker

- End every demo by handing the visitor a QR card and saying 'Try it on your own phone right now'

- Team rotation every 90 minutes: always keep 2 members at booth, 1 giving demo and 1 answering technical questions

ResolveX  |  IMPL-RX-2026-001 v2.0  |  Team Bugs  |  India Innovates 2026